## Backlog
Sprint | Story ID | Story Name | Acc Tests | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | phone number should be of 10 digit | AT01 | Done | 50 | 40 | 40 | 20 | 2015-02-26 | 2015-02-21
1 | US02 | Email id should be valid(contain @ and .) | AT02 | Done | 40 | 30 | 30 | 20 | 2015-02-26 | 2015-02-21
2 | US03 | Personal phone and work phone should not be same | AT03 | Done | 30 | 20 | 20 | 20 | 2015-03-11 | 2015-02-21
2 | US04 | Personal phone and residence phone should not be same | AT04 | Done | 30 | 20 | 20 | 10 | 2015-03-11 | 2015-02-21
2 | US05 | Work and residence phone should not be same | AT05 | Done | 30 | 20 | 20 | 10 | 2015-03-11 | 2015-02-21
2 | US06 | Name and surname should have characters only | AT06 | Done | 30 | 30 | 20 | 30 | 2015-03-11 | 2015-02-21
2 | US07 | First name should not be null. | AT07 | Done | 30 | 30 | 20 | 10 | 2015-03-11 | 2015-02-21
3 | US08 | Death date should not be before birth date | AT08 | Done | 30 | 30 | 20 | 20 | 2015-03-26 | 2015-02-21
3 | US09 | Birth date cannot be after current date | AT09 | Done | 30 | 30 | 20 | 20 | 2015-03-26 | 2015-02-21
3 | US10 | Leap year should have 29 days in february | AT10 | Done | 30 | 20 | 20 | 10 | 2015-03-26 | 2015-02-21
3 | US11 | Different sex persons can get married | AT11 | Done | 30 | 60 | 40 | 40 | 2015-03-26 | 2015-02-21
3 | US12 | Email id should be valid(contains .) | AT12 | Done | 30 | 20 | 20 | 20 | 2015-03-26 | 2015-02-21

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | phone number should be of 10 digit | Make sure that phone nmber should be of 10 digits | AT01 | 50 | 40
US02 | Email id should be valid(contains @) | Make sure that email id should be valid | AT02 | 40 | 30
US03 | Personal phone and work phone should not be same | personal phone number should be different from work phone. | AT03 | 30 | 20
US04 | Personal phone and residence phone should not be same | personal phone number should be different from residence phone. | AT04 | 30 | 20
US05 | Work and residence phone should not be same | work phone number should be different from residence phone. | AT05 | 30 | 20
US06 | Name and surname should have characters only | there should be only characters in Name and Surname. | AT06 | 30 | 30
US07 | First name should not be null. | Name should have some value. | AT07 | 30 | 30
US08 | Death date should not be before birth date | A person cannot die before he/she has born | AT08 | 30 | 30
US09 | Birth date cannot be after current date | A person's birth date cannot be after today's date | AT09 | 30 | 30
US10 | Leap year should have 29 days in february | A leap year has 29 days in february,all other years have 28 | AT10 | 30 | 20
US11 | Different sex persons can get married | Same sex marriage are prevented | AT11 | 30 | 60
US12 | Email id should be valid(contains .) | An email id must have "." in its structure | AT12 | 30 | 20
US13 | marriage to dead person should be prevented | Death date should be after marriage date
US14 | Marriage to sibling | Marriage to individual of same family individual
US15 | person cannot be married to 2 persons at a time | An individual can be married to one person at a paricular time
US16 | children's birthdate cannot be before father's | Child should be born after the father
US17 | children's birthdate cannot be before mother's | Child should be born after the mother
US18 | children's birthdate cannot be before parents turn 21 | Child should be born after parents turn 21 y/o
US19 | First name cannot be null | First name should be validly filled
US20 | same person cannot be added again | The individual id should be unique
US21 | Marriage before birth is not possible | Marriage date should be after birth date
US22 | siblings should have minimum 1 common parent | In case of step children, at least one parent should be in common
US23 | siblings should have maximum 2 common parent | child should have maximum 2 parents in common
US 25 | occupation should be none before 18 | No child is allowed to work before he/she turns 18 y/o

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Phone number should be of 10 digit | Phone number is taken as input(1234567890) | No error message | Passed
AT02 | US02 | Email id should be valid | Email id is taken as input(neel.24patel@gmail.com) | No error message | Passed
AT03 | US03 | Personal phone and work phone should not be same | Personal phone and work phone | No error message | Passed
AT04 | US04 | Personal phone and residence phone should not be same | Personal phone and residence phone | No error message | Passed
AT05 | US05 | Work and residence phone should not be same | Work phone and residence phone | No error message | Passed
AT06 | US06 | Name and surname should have characters only | First name and surname | No error message | Passed
AT07 | US07 | First name should not be null. | First name and surname | No error message | Passed
AT08 | US08 | Death date should not be before birth date | Birth date, Death date | No error message | Passed
AT09 | US09 | Birth date cannot be after current date | Birth date | No error message | Passed
AT10 | US10 | Leap year should have 29 days in february | Birth date, Death date | No error message | Passed
AT11 | US11 | Different sex persons can get married | FMAS, Sex | No error message | Passed
AT12 | US12 | Email id should be valid(contains .) | Email id is taken as input(neel.24patel@gmail.com) | No error message | Passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-26 | 25 |  | 0 | 0
2015-03-12 | 23 | 2 | 70 | 40 | 105
2015-03-26 | 18 | 5 | 100 | 80
2015-04-02 | 13 | 5 | 120 | 110 | 10.9091

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | phone number should be of 10 digit | AT01 | np,dp | Done | 50 | 40 | 40 | 20 | 2015-02-26
T01.01 | Check nmber of digits |  | np,dp
US02 | Email id should be valid(contain @) | AT02 | kp,ns | Done | 40 | 30 | 32 | 20 | 2015-02-26
T02.01 | Compare with email template |  | kp,ns | Done

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Personal phone and work phone should not be same | AT03 | dp,np | Done | 30 | 20 | 20 | 20 | 2015-03-11
T03.01 | Compare personal phone and work phone
US04 | Personal phone and residence phone should not be same | AT04 | ns,kp | Done | 30 | 20 | 20 | 10 | 2015-03-12
T04.01 | Compare work phone and personal phone
US05 | Work and residence phone should not be same | AT05 | ns,np | Done | 30 | 20 | 20 | 10 | 2015-03-11
T05.01 | compare work phone and residence phone
US06 | Name and surname should have characters only | AT06 | dp,kp | Done | 30 | 30 | 20 | 30 | 2015-03-11
T06.01 | compare name and surname
US07 | First name should not be null. | AT07 | dp,np | Done | 30 | 30 | 20 | 10 | 2015-03-11
T07.01 | check if the name is null or not.

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US08 | Name should have some value. | AT08 | np,dp | Done | 30 | 30 | 20 | 10 | 2015-03-11
T08.01 | Name shouldnot be null
US09 | A person cannot die before he/she has born | AT09 | kp,ns | Done | 30 | 30 | 20 | 20 | 2015-03-26
T09.01 | Birthdate should be before death date
US10 | A person's birth date cannot be after today's date | AT10 | ns,dp | Done | 30 | 30 | 20 | 20 | 2015-03-26
T10.01 | Today's date cannot be anybody's birthdate
US11 | A leap year has 29 days in february,all other years have 28 | AT11 | ns,kp | Done | 30 | 20 | 20 | 10 | 2015-03-26
T11.01 | Check for number of days in february
US12 | Same sex marriage are prevented | AT12 | dp,np | Done | 30 | 60 | 40 | 40 | 2015-03-26
T12.01 | Opposite sexes should be married
US13 | An email id must have "." in its structure | AT13 | kp,ns | Done | 30 | 20 | 20 | 10 | 2015-03-26
T13.01 | Follow email format